## CYB 410 Project One Stepping
Green Thumb Risk Register
Positive Risk Response Options | Exploit | Share | Monitor | Accept | Probability/Impact | PI Score
Negative Risk Response Options | Avoid | Transfer | Mitigate | Accept | 1 | 1-3 | Low
Alternative Response Options | Contingency |  |  |  | 2 | 4-6 | Moderate
[5 empty] | 3 | 7-9 | High
Note: Colors in the heat map are conditionally formatted for your use in the template. Do not modify.
Risk | Something that has not happened but might
Issue | Something that has already happened
No longer active
Risk ID | Description | Risk Trigger | Risk Category | Probability (1-3) | Impact (1-3) | PI Score | Expected Result, No Action | Risk Response Type | Response Trigger | Response Description | Expected Impact of Response
| Description of the risk | How you know the risk is becoming an issue or has reached a point that requires action. | Group defines the types of risks (technological, financial, employee, etc.) | Group-sourced rough estimate of how likely this is to occur | Group-sourced rough estimate of how significant the impact of this risk will be if/when it becomes an issue | Probability multiplied by impact | What will happen if the risk becomes an issue and no action is taken | Decision made by group on how to respond to this risk (see above in blue) | How do you know it is time to put the response into play? | What is the response? | What do you expect will result from the response?
EXAMPLE | There is a chance that the project cost will exceed the amount that the company has budgeted for the work. | If the expected work remaining will cost more than $9,000 over budget, we will need to seek additional funding from management. | Financial | 2 | 3 | 6 | We will not be able to secure funding necessary to complete the project. Work may stop before MVP has been achieved. Product may never get to market and be deemed a total failure. | Mitigate | When estimated cost for MVP is within 5K of approved project total, we will begin seeking additional funding. | Meet with key stakeholders to review finished product, total spend to date, work remaining, and expected total spend. Ask for additional funding to complete work. | Given that our team has a mostly stable velocity and a proven ability to meet commitments and deliver value, we expect the answer to be yes provided the total amount of requests is less than $25K.
Ordering Supplies | There is a chance of not having access to the supplies necessary to support the nursery (including office supplies, fertilizer, additional inventory, and so on). | The online supplier is out of stock, or their website is down; internet service interruption | operational | 2 | 2 | 4 | Without nutrients, plant growth will show stunted growth and lack of luster by the fourth day. | Mitigate | Nutrient supplies getting low or nearing three days of stock remaining. | Switch to alternative suppliers like The Growers Hut or local farm stores, or consider expedited shipping. | Stabilize supply chain to ensure consistent availability of critical nutrients, minimizing the risk to plant health and growth.
Technology | There is a chance of not being able to access the the point-of-sale (POS) system or the licensing portal for regulated items (for example, pesticides and chemicals). | POS system crash or power outage. | Technological | 2 | 2 | 4 | Sales and transaction processing would be disrupted, possibly affecting daily revenue. | Mitigate | Failure signs in hardware or software, or warnings of impending power outages. | Utilize backup laptop for POS access; ensure IT support is readily available for swift repair and recovery. | Reduce downtime and minimize revenue impact by ensuring transaction continuity.
Physical Security | There is a chance that if physical security is not in place, the opportunity for breaking and entering occurs. | Reports of nearby criminal activity or discovered vulnerabilities in current security setup. | Security | 2 | 3 | 6 | Potential theft or damage could lead to significant asset loss. | Mitigate | Increased local criminal activity or identified security gaps. | Upgrade security systems, enhance monitoring, and engage a security service. | Strengthened security to prevent unauthorized access and minimize potential losses.
Asset Management | There is a chance of loss of quality control or loss of crop due to environmental factors or growing techniques. | Inventory discrepancies or adverse weather conditions. | operational | 2 | 2 | 4 | Loss of stock leading to inability to meet sales demands. | Mitigate | Noted inventory shortages or forecasted severe weather. | Implement robust inventory management system and contingency plans for weather-related disruptions. | Ensure continuity of operations and availability of stock for sales.
Insurance | There is a chance of not having the proper insurance that would cover different situational issues related to business assets and employees. | Discovery of gaps in current insurance coverage. | Financial | 1 | 3 | 3 | Significant financial exposure in the event of disasters or accidents. | Mitigate | Annual insurance review findings. | Review and adjust insurance policies to ensure comprehensive coverage. | Financial protection against a range of potential risks, minimizing unexpected expenditures.
Safety | There is a chance there could be an opportunity for mortal danger because of the nature of the business (for example, using ladders, forklifts, and pesticides). | Safety incidents or regulatory compliance checks. | Health & Safety | 2 | 3 | 6 | Potential for serious employee injuries and possible legal ramifications. | Mitigate | Reported safety concerns or incidents. | Enhance safety training, enforce strict adherence to safety protocols, and ensure equipment is maintained. | Reduced risk of injury, compliance with health and safety regulations, and a safer work environment.